## Sheet1
Capstone project must involve a comprehensive analysis of a project management topic
Due: Submit your poster by Sunday, Week 13 (11:59 pm Central)
1 | an analytical review of project management methodologies or in-depth examination of a real/hypothetical project.
2 | Final deliverable needs to be a detailed poster presentation that will be shared with peers for critique and learning through a structured peer-reviewed process.
End Goal:
1 | Demostration of the ability to integrate and communication complex information related to the planning and execution of project management approaches and responsibilities
2 | Understanding in order to showcase the advanced project management strategies, including budgeting, scheduling, resource allocation and project monitoring and control.
Assignment Objective:
| 1 | Describe the planning and execution of a complex project incorporating a management approach. (MLO 1, 2; CLO A, E)
| 2 | Develop a comprehensive project plan that includes budgeting, scheduling, and resource allocation. (MLO 2, 2;CLO D, E)
| 3 | Analyze a complex project and develop documentation of the process for transitioning the project to operational status. (MLO1, 2; CLO D, E)
Directions
Project Selection
| 1 | Choose a topic that reflects a significant aspect of project management. This could be a detailed analysis of a completed project, a case study on the use of specific project management methodologies, or a hypothetical scenario that explores project planning and execution strategies.
| 2 | You have the option to work individually or in groups. Working in groups can enhance collaboration and bring diverse perspectives to your project. However, if you prefer to work individually, that is also acceptable.
| 3 | Project selection approved by Week 4.
Research and Analysis
| 1 | Conduct thorough research on your chosen topic. Gather data, utilize project management tools, and apply the concepts learned throughout the course. Include the following project management elements:
|  | 1 | Project introduction
|  | 2 | Planning
|  | 3 | Budgeting
|  | 4 | Scheduling
|  | 5 | Execution
|  | 6 | Monitoring
|  | 7 | Transition
| 2 | Analyze your findings, focusing on the critical aspects of project planning, execution, monitoring, and control.
| 3 | Develop a comprehensive project plan that includes budgeting, scheduling, and resource allocation.
Poster Creation
| 1 | Design a poster that thoroughly communicates your project. Include key elements such as introduction, methodology, results, and conclusions.
| 2 | Be sure to incorporate all necessary elements such as project background, analysis, results, and conclusions.
| 3 | Ensure that your poster is visually engaging and organized in a way that logically presents your analysis.
Peer Review
| 1 | Participate in the peer review process by providing constructive feedback on your classmates’ projects.
| 2 | Use the feedback received from your peers understanding of project management applications.
Due: Submit 5 Peer Reviews by Friday, Week 14 (11:59 pm Central) NOTE: Friday, Week 14 is the final day of the course.
Final Poster
Final Poster
| Criteria | Ratings | Pts
| This criterion is linked to a Learning OutcomeProject Scope & Selection | 20 ptsExcellent (A)Topic is highly relevant, clearly defined, and demonstrates strategic depth in project management. | 20 pts
(12 pts) Proficient (B)Topic is appropriate and defined with general relevance to course themes.
8 ptsBasic (C)Topic is somewhat unclear, simplistic, or loosely tied to project management.
0 ptsNeeds Improvement (D/F)Topic lacks relevance, clarity, or does not meet assignment criteria.
| This criterion is linked to a Learning OutcomeResearch & Analytical Depth | 30 ptsExcellent (A)Extensive research with strong integration of tools/data. Analysis demonstrates critical thinking and systems-level insight. | 30 pts
18 ptsProficient (B)Adequate research with sound use of tools and coherent analysis of planning and execution.
12 ptsBasic (C)Basic data and tools used; analysis is superficial or lacks specificity.
0 ptsNeeds Improvement (D/F)Minimal research and analysis; lacks logical structure or integration.
| This criterion is linked to a Learning OutcomeProject Plan & PM Components | 20 ptsExcellent (A)Fully developed plan including budgeting, scheduling, monitoring, and transition. Components are interlinked and justified. | 20 pts
12 ptsProficient (B)Includes most project components with reasonable clarity and connection to planning goals.
8 ptsBasic (C)Some components missing or loosely developed; limited coherence.
0 ptsNeeds Improvement (D/F)Project plan is incomplete, vague, or disconnected from course concepts.
| This criterion is linked to a Learning OutcomePoster Content & Design | 15 ptsExcellent (A)Poster is visually compelling, logically organized, and clearly communicates methodology, findings, and conclusions. | 15 pts
9 ptsProficient (B)Poster is organized and informative with some visual appeal and clarity of information.
6 ptsBasic (C)Poster presents necessary information but lacks visual clarity or logical flow.
0 ptsNeeds Improvement (D/F)Poster is poorly designed, hard to interpret, or missing key elements.
| This criterion is linked to a Learning OutcomeCommunication & Documentation | 10 ptsExcellent (A)Writing is precise and professional. Poster and peer review responses demonstrate mastery of project management language. | 10 pts
6 ptsProficient (B)Generally clear communication with minor errors; demonstrates sound understanding.
4 ptsBasic (C)Language is inconsistent or simplistic; ideas may be difficult to follow.
0 ptsNeeds Improvement (D/F)Writing lacks clarity, contains errors, or fails to convey core ideas.
| This criterion is linked to a Learning OutcomeEngagement in Peer Review | 5 ptsExcellent (A)Provides insightful, constructive feedback using PM principles. Demonstrates learning from peer feedback. | 5 pts
3 ptsProficient (B)Offers relevant peer critiques and acknowledges feedback impact.
2 ptsBasic (C)Limited or vague feedback; minimal engagement with peer input.
0 ptsNeeds Improvement (D/F)No peer review participation or off-topic/non-constructive feedback.

## Project Tracker
ISE 5763 Capstone — Project Requirements & Tracker
| Project Title: |  | PM methodology as an enforceable operational boundary for autonomous agents — a case study of a self-governing software project.
| Team Members: |  | Emmanuel Akinwale
| Individual / Group: |  | Individual (open to peer feedback)
| Topic / Focus: |  | Case study of a PM methodology — pm-substrate repo as implementation case study + execution analysis
Topic Approved (Wk 4):
| Progress: |  | 3 / 19 complete (16%)
# | Task / Requirement | Phase | Details / Acceptance Criteria | Owner | Due (Wk) | Status | Notes
1 | Select project topic | Selection | Detailed analysis of a completed project, a case study on a specific PM methodology, or a hypothetical project scenario. |  | 4 | Complete | Idea formulated & scored 18/20 on Project Definition sheet; selection submitted 7/19/2026.
2 | Choose individual or group | Selection | Decide whether to work individually or in a group. |  | 4 | Complete | Working individually per project write-up.
3 | Get topic approved | Selection | Project selection approved by instructor. |  | 4 | Complete | Selection submitted 7/19/2026 — awaiting instructor approval. Mark Complete and fill Topic Approved date (D8) when instructor signs off.
4 | Project introduction | Research | Background and context of the chosen project. |  |  | Not Started
5 | Planning | Research | Scope, objectives, and approach for the project. |  |  | Not Started
6 | Budgeting | Research | Cost estimates and budget allocation. |  |  | Not Started
7 | Scheduling | Research | Timeline, milestones, and dependencies. |  |  | Not Started
8 | Execution | Research | How the project work is carried out. |  |  | Not Started
9 | Monitoring | Research | Monitoring and control of progress and performance. |  |  | Not Started
10 | Transition | Research | Documentation for transitioning the project to operational status. |  |  | Not Started
11 | Analyze findings | Research | Focus on critical aspects of planning, execution, monitoring, and control. |  |  | Not Started
12 | Comprehensive project plan | Research | Includes budgeting, scheduling, and resource allocation. |  |  | Not Started
13 | Design poster | Poster | Communicate the project: introduction, methodology, results, and conclusions. |  |  | Not Started
14 | Include required elements | Poster | Project background, analysis, results, and conclusions. |  |  | Not Started
15 | Make poster visual & organized | Poster | Visually engaging and logically presented. |  | 13 | Not Started
16 | Submit poster | Poster | Submit poster by Sunday, Week 13 (11:59pm Central). |  | 13 | Not Started
17 | Provide peer feedback | Peer Review | Constructive feedback on classmates' projects. |  | 14 | Not Started
18 | Submit 5 peer reviews | Peer Review | Submit 5 peer reviews by Friday, Week 14 (11:59pm Central). |  | 14 | Not Started
19 | Incorporate feedback | Peer Review | Use peer feedback to deepen PM understanding. |  | 14 | Not Started

## Project Definition
Project Definition — Idea → Selection → Objectives → Breakdown
STEP 1 — Brainstorm candidate ideas & score them (1 = weak, 5 = strong)
Candidate Idea | PM Relevance | Data Available | Interest | Feasibility | Total
PM Substrate for Reliable AI Agent Project Workflows — pm-substrate repo as a software implementation case study + project execution analysis | 4 | 5 | 5 | 4 | 18
Tip: the highest total is your strongest candidate — carry it into Step 2.
STEP 2 — Project Selection (approval due Week 4)
Chosen topic (winner from Step 1) | PM Substrate for Reliable AI Agent Project Workflows — applying project management methods to the planning, implementation, and monitoring of the pm-substrate repository
Project type | Case study of a PM methodology
Organization / context (real or hypothetical) | Real, individually-run open-source software project: the pm-substrate GitHub repo (typed events, graph-based state, read-set validation, observation contracts, eval scenarios, Local Agents Lab Enviroment as TestBed then a Financial Hedge Fund for research and trading - which requests high in/out flow of data constantly, finance-adapter example). Peer input welcomed on scope, PM metrics, and non-technical presentation.
Why it matters to project management | AI agents often act on stale, incomplete, or non-authoritative information. This project demonstrates how core PM disciplines — budgeting, scheduling, resource allocation, execution tracking, monitoring & control, and transition to operations — keep a fast-changing technical system correct, traceable, and risk-controlled.
One-sentence topic statement | A case study applying advanced project management methods — budgeting, scheduling, resource allocation, execution monitoring, and operational transition — to the delivery of pm-substrate, an open-source system that gives AI agents a validated, current-state view of a project before they act.
Rubric target (20 pts): “highly relevant, clearly defined, demonstrates strategic depth.”
STEP 3 — Objectives (what your project must demonstrate)
Overall project objective (SMART) | By the Week 13 poster deadline, deliver an evidence-based case study of the pm-substrate project that documents: (1) a complete project plan — time/tooling budget, milestone schedule, and resource plan; (2) execution tracked through commits, tests, and changelog; (3) monitoring via build verification and eval-scenario metrics; and (4) a transition-to-operations package (versioned release + runbook) — with topic approval secured by Week 4.
| Assignment objective (from brief) |  |  | How my project addresses it
Objective 1 | Describe the planning and execution of a complex project incorporating a management approach. (MLO 1, 2; CLO A, E) |  |  | Poster narrates the full lifecycle of pm-substrate — planning (architecture, milestones, risk register) through execution (tracked code changes, tests, changelog) — under an explicit management approach: iterative delivery with stage-gate milestone reviews.
Objective 2 | Develop a comprehensive project plan that includes budgeting, scheduling, and resource allocation. (MLO 2, 2;CLO D, E) |  |  | Plan built in this workbook: time/tooling budget for implementation and testing phases; milestone schedule (research → architecture → adapter → validation rules → eval scenarios → reporting); resource plan across five roles — engineering, PM, testing, technical writing, domain review.
Objective 3 | Analyze a complex project and develop documentation of the process for transitioning the project to operational status. (MLO1, 2; CLO D, E) |  |  | Analysis of monitoring data (test results, build verification, eval metrics) plus a documented transition to operational status: versioned release, runbook/usage documentation, and acceptance criteria for ongoing use.
STEP 4 — Scope breakdown (required PM elements)
Element | What I will cover |  |  | Data / tools I'll need
Project introduction | Problem statement: AI agents act on stale, incomplete, or non-authoritative state. Introduce pm-substrate as the proposed solution and the stakeholder value of managing it as a formal project. |  |  | Repo README, project write-up, course concepts
Planning | Scope definition and WBS from milestones (research, architecture, adapter, validation rules, eval scenarios, reporting); risk register (scope creep, technical-to-PM translation); chosen management approach. |  |  | This workbook (Definition + Tracker), WBS / Gantt, risk log
Budgeting | Cost–benefit analysis: (a) cost side — estimated vs. actual hours per phase + tooling costs (budget $0 items explicitly); (b) benefit side — modeled token-cost savings from reduced agent retries (eval-measured retry rates × assumed task volume × token price), with sensitivity analysis. See Token Savings Model sheet. |  |  | Effort estimates, time log, cost table in Excel
Scheduling | Milestone schedule with dependencies and critical path, mapped to course weeks (approval Wk 4 → poster Wk 13); baseline vs. actual dates to show schedule control. |  |  | Gantt chart, Project Tracker due-weeks, GitHub milestones
Execution | Evidence of managed delivery: commits mapped to milestones, changelog updates, completed ArrowHedge adapter and read-set validation rules. |  |  | GitHub commit history, changelog, pull requests
Monitoring & control | KPIs: test pass rate, build verification, eval-scenario metrics, milestone variance, and token efficiency (tokens wasted per retry; retry rate with vs. without read-set validation) — with corrective actions when metrics slip. Token KPIs feed the budgeting benefit model. |  |  | CI/test results, eval metrics, variance table
Transition to operations | Operational-readiness package: versioned release, runbook/usage documentation, observation contracts as ongoing quality gates, and handoff/acceptance criteria. |  |  | Release notes, runbook, repo documentation
STEP 5 — Rubric alignment check (aim for the A column)
Rubric criterion | Pts | What Excellent (A) requires |  | My plan to get there
Project Scope & Selection | 20 | Highly relevant, clearly defined topic with strategic depth. |  | Lead with the Step 2 one-sentence statement; secure Week-4 approval; open the poster with the problem statement and stakeholder value so relevance and strategic depth are explicit.
Research & Analytical Depth | 30 | Extensive research, strong tools/data integration, critical systems-level analysis. |  | Use primary repo data — commit history, CI/test results, eval-scenario metrics — plus PM methodology sources. Analyze (variance, corrective actions, systems-level insight on agents/tools/state), don't just describe.
Project Plan & PM Components | 20 | Fully developed plan — budgeting, scheduling, monitoring, transition — interlinked and justified. |  | Build all six components in this workbook — budget, schedule, resources, execution, monitoring, transition — and show interlinks: monitoring KPIs trigger schedule/budget corrections; justify each design choice.
Poster Content & Design | 15 | Visually compelling, logically organized; clear methodology, findings, conclusions. |  | Poster flows left→right through the lifecycle: intro → plan → execution → monitoring → transition → conclusions. One non-technical analogy up front; visuals: Gantt, budget-vs-actual chart, KPI dashboard.
Communication & Documentation | 10 | Precise, professional writing; mastery of PM language. |  | Use precise PM vocabulary (baseline, variance, critical path, stage gate). Draft early; test clarity on a non-technical reader; proofread against the rubric before submission.
Engagement in Peer Review | 5 | Insightful, constructive feedback using PM principles; shows learning from feedback. |  | Give 5 structured peer reviews framed in PM principles (scope, schedule, risk, quality). Log feedback received and document at least one change made in response — evidence of learning.
Total | 100
Note on C6: Emmanuel Akinwale: Your note: "the project mgmt methodologies are all demonstratable." Agreed — budgeting, scheduling, resource allocation, execution, monitoring all explicitly mapped. Scored 4 not 5 because the write-up omits the required Transition-to-operations element; add it and this is a 5.
Note on D6: Emmanuel Akinwale: Excellent primary data: real repo with commits, tests, changelog, build verification, eval metrics — rare advantage for the 30-pt Research & Analytical Depth criterion.
Note on E6: Emmanuel Akinwale: Your own repo and research problem — sustained motivation through Week 13 is not a risk.
Note on F6: Emmanuel Akinwale: Individually feasible with data already in hand. Two acknowledged risks: scope creep, and translating an AI-agent problem into PM language for a non-technical poster audience.
Note on C38: Emmanuel Akinwale: Source: Final Poster rubric on Sheet1 (rows 52-55)
Note on C39: Emmanuel Akinwale: Source: Final Poster rubric on Sheet1 (rows 56-59)
Note on C40: Emmanuel Akinwale: Source: Final Poster rubric on Sheet1 (rows 60-63)
Note on C41: Emmanuel Akinwale: Source: Final Poster rubric on Sheet1 (rows 64-67)
Note on C42: Emmanuel Akinwale: Source: Final Poster rubric on Sheet1 (rows 68-71)
Note on C43: Emmanuel Akinwale: Source: Final Poster rubric on Sheet1 (rows 72-75)

## Token Savings Model
Token Cost–Benefit Model — Modeled Savings from pm-substrate
MODELED, NOT MEASURED — savings are illustrative under the stated assumptions. Replace blue inputs with eval-scenario measurements as they become available.
Assumptions (blue = inputs)
Agent task volume (tasks / month) | 1000
Retry rate — baseline (no substrate) | 25%
Retry rate — with pm-substrate | 8%
Avg tokens wasted per retry | 15000
Token price ($ per 1M tokens, blended) | 3
Modeled savings (formulas)
Retries avoided / month | 170
Tokens saved / month | 2550000
$ saved / month | 7.65
$ saved / year | 91.8
Sensitivity — $ saved / year: task volume × token price
Tasks/mo ↓ · $ per 1M tokens → | 1 | 2 | 3 | 4 | 5
250 | 7.65 | 15.3 | 22.95 | 30.6 | 38.25
500 | 15.3 | 30.6 | 45.9 | 61.2 | 76.5
1000 | 30.6 | 61.2 | 91.8 | 122.4 | 153
2000 | 61.2 | 122.4 | 183.6 | 244.8 | 306
4000 | 122.4 | 244.8 | 367.2 | 489.6 | 612
Note on C6: Emmanuel Akinwale: Assumption — illustrative workload for the business case. State this on the poster.
Note on C7: Emmanuel Akinwale: PLACEHOLDER — replace with measured retry/failure rate from eval scenarios run WITHOUT read-set validation.
Note on C8: Emmanuel Akinwale: PLACEHOLDER — replace with measured retry/failure rate from eval scenarios run WITH read-set validation + observation contracts.
Note on C9: Emmanuel Akinwale: PLACEHOLDER — replace with measured mean (prompt + completion tokens) per failed/retried attempt from the token meter.
Note on C10: Emmanuel Akinwale: Assumption — blended input/output price. Cite your provider's published price sheet on the poster and in the poster references.